|  | MySeedBook DOWNLOAD-TO-PAID GROWTH PLAN |
| --- | --- |

# A 90-Day Plan to Increase
Downloads, Active Users, and Paid Subscriptions

Positioning • App Store Optimization • Activation • Retention • Monetization

Prepared for Chandra's Essentials

June 30, 2026

|  | Primary strategic focus Position MySeedBook as the digital seed binder for gardeners whose collections have outgrown a shoebox — then optimize every step from discovery to download, activation, retention, and paid conversion. |
| --- | --- |

# How to Use This Plan

This document converts the current download challenge into a practical operating plan. The first two weeks are focused on fixing conversion and trust. The next six weeks build a repeatable organic acquisition engine. The final month introduces carefully measured paid growth.

## Contents

Executive Summary and Current Baseline

1. Logo and App Icon Recommendation

2. Positioning and Target Customer

3. App Store Listing and ASO

4. Screenshots and Store Video

5. Trust, Privacy, and Brand Consistency

6. Pricing and Product Packaging

7. Activation, Retention, and Subscription Conversion

8. The 90-Day Growth Roadmap

9. Content Marketing System

10. Partnerships and Community Outreach

11. Paid Acquisition and Campaign Tracking

12. KPI Dashboard and Decision Rules

13. Landing Page Requirements

14. What Not to Do

15. Immediate Action Checklist

Appendices: Store Copy, Outreach Copy, Weekly Cadence, and Sources

## First Seven Actions

Replace the app icon with a simplified book-and-sprout symbol.

Rename the store listing to “MySeedBook: Seed Inventory.”

Replace the first three store screenshots with benefit-led, readable screens.

Audit the Apple age rating and both stores’ privacy declarations.

Reduce and simplify subscription pricing and product names.

Add activation, paywall, trial, and purchase analytics.

Recruit 25 Founding Gardeners who own real seed collections.

|  | The message to own Do not market MySeedBook as another general gardening app. Market it as the easiest way to turn a messy seed collection into a searchable digital seed binder. |
| --- | --- |

# Executive Summary and Current Baseline

Seventeen downloads do not mean MySeedBook is a bad app. They indicate that the app was published without a strong enough distribution and conversion system. The current priority is not adding more unrelated features. It is building a measurable funnel from qualified discovery to repeat usage and paid conversion.

|  | Growth funnel Discovery → Product-page view → Download → First seed added → Five seeds added → Return visit → Paywall → Trial or purchase |
| --- | --- |

## Owner-Supplied Snapshot

| Metric | Current | Interpretation |
| --- | --- | --- |
| Apple impressions | 321 | How often the listing appeared |
| Apple product-page views | 32 | People who opened the listing |
| Apple first-time downloads | 5 | New downloads in the snapshot |
| Google Play total installs | 12 | Total shown in the supplied Play Console view |
| Combined downloads / installs | 17 | Current cross-store baseline |
| Apple impression → page-view rate | ≈10.0% | 32 ÷ 321 |
| Apple page-view → download rate | ≈15.6% | 5 ÷ 32 |

Apple App Store Connect analytics provided by the owner, June 2026.

## What the Numbers Say

The store page can convert some qualified visitors, but the overall volume of qualified traffic is extremely low.

The product-page view rate indicates that the icon, title, keyword match, and search presentation need improvement.

There is not yet enough user volume to make reliable conclusions about subscription demand.

The first meaningful milestone is 100 activated users — people who add several real seed records — not merely 100 installs.

## 90-Day Outcome

The purpose of this plan is to establish a repeatable customer-acquisition system, prove that new users reach the first value moment quickly, and validate a paid offer that feels reasonable for an early-stage gardening utility.

# 1. Logo and App Icon Recommendation

|  | Recommendation Keep the logo concept. Redesign the app icon. |
| --- | --- |

The open book and seedling are appropriate, distinctive, and aligned with the brand meaning: the book represents knowledge and the seedling represents growth. The issue is not the concept; it is how the current artwork performs at small app-icon sizes.

## Why the Current Icon Underperforms

The word “MySeedBook” becomes difficult to read at 32–60 pixels.

The border, corner ornaments, leaves, book, sprout, and wordmark compete for attention.

At small sizes it reads more like a miniature product label than a recognizable app symbol.

A simplified symbol will contrast better against white App Store and Google Play screens.

## Recommended App Icon Brief

| Element | Direction |
| --- | --- |
| Background | Deep garden green (#3A4A2C) |
| Main symbol | Cream / seed-paper-beige open book |
| Growth symbol | One bold seedling rising from the center |
| Text | No words inside the app icon |
| Detail level | No ornamental corner border; thicker lines |
| Color count | Two colors, or three at most |
| Scale | Book and seedling fill approximately 65–75% of the icon |

## Where to Keep the Full Logo

Website headers

Email and printed materials

Onboarding and splash screens

Social profiles where the mark appears at a larger size

## Simple Recognition Test

Create three icon options and show them at 32 × 32 pixels to approximately 15 gardeners. Ask the following questions:

What do you think this app does?

Which icon would you tap first?

Which icon looks most trustworthy?

Which icon can you recognize after looking away?

Do not ask which version is the prettiest. Test comprehension, recognition, and trust.

# 2. Positioning and Target Customer

MySeedBook currently has several capabilities: seed cataloging, garden notes, supplier tracking, weather, calendar tools, voice notes, cloud sync, and AI. Those capabilities may be valuable, but presenting all of them at the same level weakens the initial message.

|  | Positioning statement The digital seed binder for gardeners whose seed collection has outgrown a shoebox. |
| --- | --- |

## Primary Target Customer

Home gardeners with approximately 20–100+ seed packets

Vegetable and flower gardeners who purchase seeds repeatedly

Seed savers and homesteaders

Community gardeners and seed-library participants

Gardeners who forget what they own or where they purchased it

People currently using paper, spreadsheets, drawers, bins, or shoeboxes

## Core Promise

|  | Primary promise Know every seed you own, where it came from, and what to plant next. |
| --- | --- |

## Best Marketing Problem

|  | Customer pain Stop buying seeds you already own. |
| --- | --- |

This problem is immediate, easy to understand, and financially useful. Weather, AI, voice notes, suppliers, and calendars should support this promise rather than compete with it.

# 3. App Store Listing and ASO

The Apple and Google listings should tell one consistent story. Use American spelling (“catalog”) in US-facing copy. The internal bundle identifier does not need to change.

## Recommended Metadata

| Field | Recommended Copy |
| --- | --- |
| App name | MySeedBook: Seed Inventory |
| Apple subtitle | Garden Journal & Planner |
| Google short description | Catalog seeds, track suppliers, and plan planting seasons with confidence. |
| Primary category message | Seed inventory and garden recordkeeping |

## Recommended Apple Promotional Text

|  | Turn every seed packet into an organized, searchable garden record. Track varieties, suppliers, planting dates, notes, weather, and more — all in one calm garden journal. |
| --- | --- |

## Suggested Apple Keyword Field

packet, organizer, planting, calendar, sowing, harvest, supplier, collection, vegetable, flower, notes

## Recommended Description Opening

|  | You have seed packets in drawers, shoeboxes, and bags from last season. MySeedBook turns them into a searchable seed inventory, so you always know what you own, where it came from, and what to plant next. Add photos, varieties, suppliers, purchase details, planting dates, and garden notes. Search your collection before buying more seeds, plan upcoming planting seasons, and keep your garden information with you wherever you go. |
| --- | --- |

## Listing Rules

Lead with the customer problem and result before listing features.

Use the same product naming and benefit hierarchy on Apple and Google.

Only advertise features that are currently available and working.

Remove duplicated wording, fragmented sentences, and technical product names.

Make the first three lines understandable without scrolling.

# 4. Screenshots and Store Video

The first screenshots must explain the product immediately. The current visual style is cohesive, but the interface is sometimes too small, angled devices reduce readability, and decorative artwork occupies space that should demonstrate product value.

## Recommended Screenshot Sequence

| Order | Headline | Primary Visual |
| --- | --- | --- |
| 1 | Know Every Seed You Own | Large, readable inventory screen |
| 2 | Stop Buying Duplicate Seeds | Search / filter results with similar seed varieties |
| 3 | Plan What to Plant Next | Planting calendar and weather |
| 4 | Remember Where Every Seed Came From | Supplier history |
| 5 | Add Notes While You Garden | Voice notes, only if fully working |
| 6 | Your Garden Records, Synced and Safe | Cloud sync / multi-device benefit |
| 7 | Unlock Unlimited Seed Records | Paid-plan value |

## Screenshot Design Rules

One headline of five to eight words

One large, upright phone

One primary app screen

No paragraph copy

One small botanical accent

Use Sage on only two or three slides and never cover the interface

## 15–20 Second Store Video

| Timing | Scene |
| --- | --- |
| 0–3 sec | Messy seed box and duplicate packets |
| 3–7 sec | Search the digital inventory |
| 7–11 sec | Add a seed and photo |
| 11–15 sec | Show calendar or weather |
| 15–18 sec | “Know what you own. Plant with confidence.” |

Use real hands and real seed packets. Sage can appear at the end, but real gardening material will create more trust than using only animated content.

# 5. Trust, Privacy, and Brand Consistency

Trust issues affect downloads and paid conversion. The public experience should look like one product from one company with accurate privacy, support, and age-rating information.

## Privacy and Age-Rating Audit

Compare store declarations with the actual behavior of Supabase, RevenueCat, PostHog, weather services, photo uploads, voice features, and external supplier links.

Confirm whether the app truly contains unrestricted web access or public user-generated content.

Correct inaccurate declarations, but never lower a rating or remove data disclosures unless the product behavior supports the change.

Use a branded privacy-policy page that accurately describes MySeedBook.

## Standardize the Public Identity

| Area | Recommended Standard |
| --- | --- |
| Brand line | MySeedBook by Chandra’s Essentials |
| Support email | support@chandrasessentials.com |
| Website role | Dedicated MySeedBook landing page under the existing domain |
| Support experience | One help address and consistent company naming |

# 6. Pricing and Product Packaging

The current annual prices are aggressive for a new app with limited ratings, limited proof of recurring value, and a small user base. The paid structure should be easier to understand and aligned with continuing customer benefit.

## Recommended Pricing Structure

| Plan | Price | Included Value |
| --- | --- | --- |
| Free | $0 | Up to 20 seeds; basic photos and notes; local use |
| Essential Monthly | $3.99 | Unlimited seeds, cloud sync, suppliers, calendar, export |
| Essential Annual | $29.99 | Same as monthly with annual discount |
| Garden Pro Monthly | $5.99 | Essential plus voice, AI, packet assistance, advanced weather |
| Garden Pro Annual | $44.99 | Same as monthly with annual discount |
| Founding Lifetime Essential | $49.99 | Essential features only; exclude ongoing AI usage |

## Packaging Rules

Do not sell lifetime access to unlimited AI or transcription because those features create ongoing costs.

If paying subscribers already exist, grandfather their access and communicate changes carefully.

Use customer-facing names such as Essential and Garden Pro instead of technical identifiers such as “Voice Annual.”

Make the upgrade about a gardening outcome, not the underlying technology.

# 7. Activation, Retention, and Subscription Conversion

Marketing cannot compensate for weak activation. A new user should understand the value in seconds, add a first seed within two minutes, and experience a useful result during the first session.

## Activation Goal

| Stage | Desired Behavior |
| --- | --- |
| Step 1 | Understand the app’s purpose in under 10 seconds |
| Step 2 | Add the first seed within two minutes |
| Step 3 | Add at least three seeds in the first session |
| Step 4 | Experience one useful outcome: search, planting date, supplier, weather, or notes |

Preload one example seed so the inventory never feels empty.

## Onboarding

|  | Ask one question What would you most like to organize? |
| --- | --- |

My seed packets

My planting schedule

My suppliers

My garden notes

Take the person directly to the selected action. Do not begin with a long feature tour.

## Paywall Timing

| Trigger | Message / Action |
| --- | --- |
| At 8 seeds | Show progress: “You have organized 8 of 20 free seed records.” |
| At 15 seeds | Preview unlimited inventory and cloud backup |
| At seed 21 | Present the upgrade |
| Trial timing | Offer a seven-day Garden Pro trial after the user experiences the catalog |

|  | Paywall headline Your seed collection has outgrown the free plan. |
| --- | --- |

## Retention Features That Support a Subscription

Seeds ready to plant this week

Frost or weather warning

Seed records missing planting dates

Seeds nearing expected storage life

Monthly inventory summary

“You already own this variety” when searching a wishlist

## Review Prompt Timing

After adding the fifth seed

After completing the first planting plan

After returning on a later day

After successfully restoring or syncing records

Do not compensate users for positive reviews. Founding users may receive access in exchange for product feedback, not for store ratings.

# 8. The 90-Day Growth Roadmap

## Days 1–14: Repair the Conversion System

Primary goal: make the app credible and measurable before driving traffic.

Simplified app icon

New app name and subtitle

New first three screenshots

Consistent Apple and Google descriptions

Privacy and age-rating audit

Simplified pricing and customer-friendly plan names

One support email and dedicated landing page

Analytics events for activation and purchases

In-app review prompt

|  | Do not do this yet Do not purchase broad advertising during the first two weeks. |
| --- | --- |

### Events to Track

onboarding_started
onboarding_completed
first_seed_added
third_seed_added
fifth_seed_added
calendar_used
supplier_added
paywall_viewed
trial_started
purchase_completed
subscription_renewed
subscription_cancelled

## Days 15–30: Founding Gardeners Launch

Recruit 25 target gardeners — not general app testers. Each participant should own at least 20 seed packets, add at least 10 genuine records, use the app for two weeks, complete a short survey, and allow observation of one onboarding session. Offer six or twelve months of Essential access for product feedback.

### Research Questions

How do you organize seeds today?

What made adding a seed frustrating?

Which field felt unnecessary?

What did you expect the app to do but could not find?

Which benefit would justify $29.99 per year?

Would you prefer annual, monthly, or lifetime Essential?

What would make you reopen the app next week?

### Day-30 Target

50 cumulative new installs

30 users add at least one seed

20 users add at least five seeds

5–10 honest ratings or reviews

At least 3 usable testimonials

First 1–3 paid customers

## Days 31–60: Build Repeatable Acquisition

### Weekly Organic Cadence

Three short vertical videos

Five Pinterest pins

One Instagram carousel

One email or blog article

Ten partnership outreach messages

Reuse the same core content across channels rather than creating separate material for every platform.

### Seed Box Reset Challenge

Gather every seed packet.

Remove empty or damaged packets.

Sort by vegetables, flowers, and herbs.

Add the first ten to MySeedBook.

Record suppliers and purchase dates.

Add upcoming planting dates.

Review the completed digital catalog.

Create a free Seed Inventory Starter Sheet containing QR codes for both app stores. The printable captures email leads and serves gardeners who are not ready to install immediately.

### Day-60 Target

150 cumulative installs

75 activated users

20 ratings or reviews

5–8 paying customers

At least two partnerships with a garden club, seed library, nursery, or creator

## Days 61–90: Scale What Works

Repeat the two highest-performing content formats.

Stop channels generating installs but no seed records.

Publish customer before-and-after seed-box stories.

Launch a referral program.

Test tightly controlled paid search.

Create a seasonal landing page for fall planting.

Prepare a winter seed-inventory campaign.

### Day-90 Target

300–500 cumulative installs

150–250 activated users

30+ ratings or reviews

8–15 paying subscribers

25% or better seven-day retention

One identifiable acquisition channel that produces users repeatedly

These are operating targets, not guarantees. The first 90 days are for proving that the funnel can work.

# 9. Content Marketing System

The strongest content will show a real gardening problem and a visible transformation. Use real seed packets, your hands, your garden, and the actual app screen. Sage can support the story, but founder-led and product-led demonstrations should carry most of the trust.

## Best Content Hooks

“Before you buy another seed packet, check this.”

“I bought the same tomato seeds three times.”

“How many seeds are hiding in your kitchen drawers?”

“Your seed box needs a search bar.”

“What I record from every seed packet.”

“How I organize 30 seed packets without a spreadsheet.”

“Three things to check before ordering fall seeds.”

“I built an app because my seed collection got out of control.”

## Three Content Pillars

| Pillar | Examples |
| --- | --- |
| Seed-collection pain | Duplicates, missing packets, faded labels, bags, bins, and shoeboxes |
| Product demonstration | One action per video: add, search, supplier, planting date, voice note, weather |
| Seasonal gardening utility | Fall planning, midseason notes, seed saving, supplier reorders, winter inventory |

## Repurposing Workflow

| Source Asset | Repurposed Output |
| --- | --- |
| 1 core demonstration video | Instagram Reel / Facebook Reel / YouTube Short |
| 3 still frames | Pinterest pins |
| 5 teaching points | Instagram carousel |
| Expanded explanation | Email or blog article |
| One customer question | Community post or FAQ |

# 10. Partnerships and Community Outreach

## Qualified Partner Types

Local garden clubs

County Master Gardener groups

Community gardens

Seed libraries and seed-swap organizers

Independent nurseries and small seed sellers

Gardening newsletter owners

Gardening creators with approximately 2,000–25,000 followers

Homesteading and vegetable-gardening educators

## Outreach Message

|  | Subject: Free seed inventory access for your gardening community Hi [Name], I’m the founder of MySeedBook, a seed-inventory and garden-journal app built to help gardeners organize seed packets, suppliers, planting dates, and notes. I’m inviting a small group of garden clubs and seed communities to receive complimentary Essential access and a short product demonstration. I’m looking for honest feedback from gardeners with real seed collections — not paid endorsements. I would be glad to provide your members with a Seed Box Reset worksheet and a dedicated access code. Thank you, Chandra MySeedBook by Chandra’s Essentials |
| --- | --- |

Ask permission before posting in Facebook or Reddit communities. Do not repeatedly drop store links into groups.

# 11. Paid Acquisition and Campaign Tracking

Paid marketing should begin only after the store page, onboarding, analytics, and pricing are repaired. The objective is not the cheapest install; it is the lowest sustainable cost per activated user and paid customer.

## Apple Search Advertising Test

| Setting | Recommendation |
| --- | --- |
| Budget | $5 per day |
| Test length | 14 days |
| Geography | United States |
| Placement | Search results |
| Keyword style | Exact or tightly controlled |
| Optimization metric | Cost per activated user |

### Suggested Search Terms

seed inventory

seed tracker

seed organizer

garden journal

planting planner

seed catalog

garden record

seed collection

Pause a keyword when it generates several installs but no one adds three seeds.

## Delay Broad Google App Campaigns

Broad Google App campaigns are more useful after meaningful in-app conversion events exist and there is enough activity for the campaign to learn what a valuable user looks like. Do not optimize only for inexpensive installs.

## Campaign Tracking

Create a unique tracked link or QR code for Instagram.

Create a unique tracked link or QR code for Pinterest.

Create a unique tracked link or QR code for Garden-club outreach.

Create a unique tracked link or QR code for Printable worksheet.

Create a unique tracked link or QR code for Each creator.

Create a unique tracked link or QR code for Apple ads.

Create a unique tracked link or QR code for Email.

# 12. KPI Dashboard and Decision Rules

The following are working targets for MySeedBook, not claimed industry averages. Use them to determine where the funnel is breaking and what to fix next.

| Funnel Step | Initial Target |
| --- | --- |
| Product-page view → install | 25%+ |
| Install → onboarding complete | 70%+ |
| Install → first seed | 60%+ |
| First seed → five seeds | 40%+ |
| Seven-day retention | 25%+ |
| Activated user → paywall view | 25%+ |
| Activated user → paid | 3–5% |
| Cost per activated user | Under $3–$5 |
| Cost per paid subscriber | Under $10–$12 initially |
| Store rating | 4.5+ after sufficient reviews |

## Do Not Scale Paid Marketing Until

At least 60% of installers add one seed.

At least 25% of activated users return within seven days.

Some activated users purchase without personal encouragement from the founder.

## Decision Rules

| Observed Problem | Primary Response |
| --- | --- |
| Low impressions | Improve keywords, category relevance, icon, partnerships, and outbound traffic |
| Good views, low installs | Fix screenshots, title, description, trust, rating, and price signals |
| Good installs, low first-seed rate | Fix onboarding and first-entry workflow |
| Good activation, low return rate | Add reminders, seasonal utility, and clearer recurring value |
| Good retention, low paywall views | Improve upgrade triggers and free-plan boundary |
| Good paywall views, low purchases | Fix price, package, trial, proof, and paywall message |

# 13. Landing Page Requirements

Use the existing Chandra’s Essentials domain. A separate paid domain is not required. Create a focused MySeedBook page that can convert visitors arriving from Pinterest, social media, search, garden clubs, and creator partnerships.

Hero: “Know every seed you own.”

15-second demo video

Apple and Google download buttons

Three primary benefits

Real, readable screenshots

Free vs. Essential vs. Garden Pro comparison

Founding-gardener testimonials

Seed Box Reset printable

Frequently asked questions

Privacy and support links

Founder story

# 14. What Not to Do

Do not completely replace the MySeedBook brand.

Do not keep a text-heavy app icon.

Do not advertise broadly before fixing the store page and onboarding.

Do not add unrelated features until the seed-inventory flow retains users.

Do not describe unfinished features in the listings.

Do not maintain $69.99–$79.99 annual pricing without stronger proof and recurring value.

Do not use only animated promotional content; show real seed packets and the actual product.

Do not evaluate success using download count alone.

Do not ask friends or testers for artificial positive reviews.

Do not mix test-track installations with organic production acquisition in reporting.

# 15. Immediate Action Checklist

| Done | Action | Timing |
| --- | --- | --- |
| ☐ | Finalize three simplified icon concepts | Week 1 |
| ☐ | Select and publish the simplified icon | Week 1–2 |
| ☐ | Update app name, subtitle, short description, and long description | Week 1 |
| ☐ | Create the first three benefit-led screenshots | Week 1 |
| ☐ | Audit privacy declarations and Apple age rating | Week 1 |
| ☐ | Standardize company name, email, and privacy links | Week 1 |
| ☐ | Implement the recommended free / Essential / Garden Pro packaging | Week 2 |
| ☐ | Add analytics events from onboarding through purchase | Week 2 |
| ☐ | Build a focused MySeedBook landing page | Week 2 |
| ☐ | Recruit 25 Founding Gardeners | Weeks 2–3 |
| ☐ | Launch the Seed Box Reset Challenge | Weeks 4–5 |
| ☐ | Begin weekly content and partner outreach cadence | Ongoing |
| ☐ | Test Apple search ads after activation metrics are healthy | Weeks 8–10 |

|  | Central recommendation Build the market around one clear job: turning a messy seed collection into a searchable digital seed binder. That message can earn qualified downloads, repeat use, and a credible reason to upgrade. |
| --- | --- |

# Appendix A: Copy-Ready Store and Marketing Text

## App Name

|  | MySeedBook: Seed Inventory |
| --- | --- |

## Apple Subtitle

|  | Garden Journal & Planner |
| --- | --- |

## Google Short Description

|  | Catalog seeds, track suppliers, and plan planting seasons with confidence. |
| --- | --- |

## Promotional Text

|  | Turn every seed packet into an organized, searchable garden record. Track varieties, suppliers, planting dates, notes, weather, and more — all in one calm garden journal. |
| --- | --- |

## Paywall Headline

|  | Your seed collection has outgrown the free plan. |
| --- | --- |

## Primary Social Message

|  | Stop buying seeds you already own. Know every seed in your collection, where it came from, and what to plant next. |
| --- | --- |

# Appendix B: Weekly Marketing Operating Rhythm

| Day | Primary Activity |
| --- | --- |
| Monday | Review funnel metrics; choose the week’s customer problem |
| Tuesday | Record one core product demonstration video |
| Wednesday | Publish short video; create Pinterest variations |
| Thursday | Publish carousel or article; send five partner messages |
| Friday | Publish second short video; send five more partner messages |
| Saturday | Show the app in a real gardening workflow |
| Sunday | Review comments, user questions, installs, and activation events |

## Weekly Review Questions

Which source produced the most first-seed events?

Which content produced saves, shares, or qualified comments?

Where did users stop during onboarding?

What did Founding Gardeners ask for repeatedly?

Did paid traffic create activated users or only installs?

What will be stopped, repeated, or improved next week?

# Appendix C: Reference Links

The plan was developed from the owner-provided analytics, the current MySeedBook brand direction, the public app-store listings referenced in the original analysis, and official platform guidance. Store prices, policies, and public listing details should be rechecked before implementation because they can change.

| • Google Play listing — MySeedBook: Seed Catalogue | • Apple App Store listing — MySeedBook |
| --- | --- |
| • Chandra’s Essentials website | • Apple — App Store product page guidance |
| • Apple — Product Page Optimization | • Apple — Campaign links |
| • Apple — App information reference | • Google Play — Store listing best practices |